# 9-1-1 Funding Advisor Operational Framework

Post-Contract Award Processes, Requests & Documentation (Effective ~September 2026 onward)

Based on RFP 26-16743 (9-1-1 Call Processing Equipment – CPE) and associated Attachments (11, 14, 15, 16, TD284, TD e-288). This framework depicts the most common internal processes, external/internal requests that trigger them, sequential workflows, typical timelines, and the key forms/documents used by County-assigned CA 9-1-1 Branch Funding Advisors.

# 1. Top 10 Most Common Internal Processes

Ranked by estimated frequency and operational impact in the post-award execution phase (after master contract award and PSAPs begin ordering from awarded vendors).

| # | Process Name | Key Tasks & Sub-Tasks | Key Forms / Documents | Typical Timeline |
| --- | --- | --- | --- | --- |

| 1 | Advance CPE Funding Notification Processing & Allotment Issuance | • Receive & log Advance Notification form (Attachment 11) • Verify completeness & PSAP eligibility • Review Cloud vs On-Prem selection • Determine/calculate allotment amount per funding guidelines • Create/issue TD e-288 tracking record • Notify PSAP of allotment decision & next steps • Update internal county tracker | • Advance Notification for CPE Funding (Att. 11) • TD e-288 (Funding Authorization/Tracking) • Internal Allotment Log / Tracker | Acknowledgment: 1-2 business days Full decision/allotment: 5-10 business days |
| --- | --- | --- | --- | --- |

| 2 | SOW Review, Coordination & Approval | • Receive draft SOW from Vendor or PSAP • Check completeness vs Attachment 16 template (all sections a-m) • Verify equipment list, pricing, maintenance costs, schedule, responsibilities • Coordinate technical review (if needed with NG9-1-1 team) • Ensure alignment with awarded contract pricing (Exhibit C) • Return comments or approved version • Confirm Cloud vs On-Prem design details | • Sample SOW Template (Att. 16) • Vendor draft SOW + Quote • TD e-288 reference • Change Order Form (if revisions needed) | Initial review: 3-5 days Full coordination & approval: 7-15 business days |
| --- | --- | --- | --- | --- |

| 3 | TD e-288 Management, Tracking & Amendment | • Create new TD e-288 record upon allotment • Link to specific PSAP project & vendor • Monitor cumulative spend vs approved total • Process amendments for approved change orders • Update status (Active, In Progress, Complete, On Hold) • Provide status to PSAP/Vendor upon request • Reconcile with invoice payments | • TD e-288 Form / Tracking Record • Change Order documentation • Invoice copies (for reconciliation) • Internal Project Tracker | Initial creation: Same day as allotment Amendments: 2-5 days after approval Ongoing monitoring: Continuous |
| --- | --- | --- | --- | --- |

| 4 | Change Order Review & CA 9-1-1 Branch Approval | • Receive Change Order Request from Vendor (via PSAP or direct) • Assess impact on scope, cost, timeline, funding • Coordinate review with PSAP authorized rep • Approve, reject, or negotiate revised terms • Update TD e-288 if additional funding required • Document decision and rationale • Distribute approved change order to all parties | • Vendor Change Order Form • Original SOW (for comparison) • TD e-288 (for amendment) • Email approval record / Branch sign-off | Review & decision: 3-7 business days Complex changes: 7-14 days TD e-288 update: 1-2 days after approval |
| --- | --- | --- | --- | --- |

| 5 | Invoice Verification, Triage & Payment Coordination | • Monitor CA911Invoicing@caloes.ca.gov inbox (or county queue) • Verify invoice format per Attachment 14/15 instructions • Cross-check line items vs approved TD e-288 amount • Confirm System Acceptance Date & service period • Validate against current SOW / Change Orders • Flag discrepancies and request corrections • Coordinate approval or forward to central Finance for payment • Update project financial tracking | • CPE Service Invoice Template (Att. 15) • Invoice Instructions (Att. 14) • TD e-288 • SOW + Change Orders • TD284 Acceptance (for final payments) | Initial triage: 1-2 business days Verification & resolution: 3-7 days Payment processing: Per Finance cycle (after clean invoice) |
| --- | --- | --- | --- | --- |

| 6 | Project Timeline Monitoring & Internal/External Status Reporting | • Maintain county/PSAP project tracker or dashboard • Update milestones from approved SOW schedule • Flag delays or risks (site readiness, integration issues) • Produce monthly/quarterly status reports for supervisor • Respond to ad-hoc status requests from PSAP or leadership • Share high-level status with PSAP (upon request) • Escalate systemic issues to Branch leadership | • Internal Project Status Tracker / Dashboard • SOW Installation Schedule (section h) • Monthly Status Report template • Email status updates | Ongoing daily/weekly updates Formal internal reports: Monthly Ad-hoc responses: 1-3 business days |
| --- | --- | --- | --- | --- |

| 7 | Acceptance Testing Coordination (TD284) | • Confirm TD284 checklist is provided/used (Chapter III Funding Manual) • Coordinate testing schedule between PSAP, Vendor, and any required observers • Ensure all test scenarios covered (call flow, failover, integrations, recording) • Collect formal sign-off from authorized PSAP representative • Update project records with acceptance date • Trigger start of maintenance billing period • Handle any punch-list items post-acceptance | • System Acceptance Checklist (TD284) • SOW section d (Acceptance Testing) • Test result documentation • Formal Acceptance Sign-off form | Testing window: Per SOW schedule (typically 5-10 days) Sign-off collection: 1-3 days after successful tests Record update: Same day as sign-off |
| --- | --- | --- | --- | --- |

| 8 | Post-Acceptance MACs (Moves/Adds/Changes) Handling | • Log MAC request from PSAP or Vendor • Classify as Minor (covered under monthly maintenance) or Major (requires change order) • For minor: Confirm with Vendor & update records • For major: Route through Change Order process (Process 4) • Update SOW / TD e-288 as needed • Ensure no impact on overall funding or timeline without approval | • MAC Request Form / Email • Original SOW • Change Order Form (if major) • Updated TD e-288 (if funding impacted) | Minor MACs: 1-3 business days Major MACs: Follow Change Order timeline (3-14 days) |
| --- | --- | --- | --- | --- |

| 9 | Training Coordination & Documentation | • Confirm training dates and content per approved SOW (section k) • Coordinate logistics with PSAP and Vendor • Collect attendance / sign-off sheets • Verify delivery of user manuals, quick reference guides, and technical docs • Follow up on post-training questions or issues • Update project file with training completion | • SOW Training Plan (section k) • Training Attendance/Sign-off Form • User Manuals & Quick Reference Guides • Training completion record in project file | Coordination: 5-10 days before scheduled date Documentation: Within 2 days of completion |
| --- | --- | --- | --- | --- |

| 10 | Project Closeout, Archiving & Compliance Preparation | • Verify all deliverables complete (installation, testing, training, documentation) • Confirm final invoice paid and reconciled to TD e-288 • Collect and archive complete project file (SOW, TD284, invoices, change orders, acceptance) • Update county history / master tracker • Prepare documentation for potential audits • Decommission any temporary parallel systems if applicable • Close TD e-288 record as “Complete” | • Full Project File (all prior documents) • Final Invoice + Payment Record • TD284 Acceptance • Closeout Checklist (internal) • Archive index / retention log | Closeout activities: 5-10 business days after final acceptance & payment Archiving: Within 10 business days of closeout |
| --- | --- | --- | --- | --- |

# 2. Top Requests (External & Internal) & Linkage to Processes

Requests are the primary triggers for most processes. Below are the top 10 most common requests, categorized as External (primarily from PSAPs and Vendors) and Internal (from within Cal OES / CA 9-1-1 Branch). Each shows the triggered process, sequential steps, and realistic timeline.

## 2.1 Top External Requests (PSAPs, Vendors, Other Branches)

| # | Request Description & Source | Triggers Process | Sequential Steps & Actions | Typical Timeline |
| --- | --- | --- | --- | --- |

| E1 | PSAP submits completed Advance Notification for CPE Funding form (Cloud or On-Prem selection) to assigned advisor | Process 1 (Advance Notification & Allotment) | 1. Log receipt & send acknowledgment 2. Review for completeness & eligibility 3. Determine allotment amount 4. Create TD e-288 5. Notify PSAP of decision & next steps (vendor evaluation window) | Acknowledgment: 1-2 bus. days Full response: 5-10 bus. days PSAP then has time to evaluate awarded vendors |
| --- | --- | --- | --- | --- |

| E2 | PSAP or Vendor submits draft SOW for review/approval (per Attachment 16 template) | Process 2 (SOW Review) | 1. Perform completeness check vs template 2. Verify pricing & schedule alignment 3. Technical review (if needed) 4. Return comments or approved SOW 5. Link to TD e-288 | Initial review: 3-5 days Full approval: 7-15 bus. days PSAP signs off before installation begins |
| --- | --- | --- | --- | --- |

| E3 | Vendor submits Change Order Request (scope/cost/timeline change) requiring Branch approval | Process 4 (Change Order) | 1. Log & assess impact 2. Coordinate with PSAP for concurrence 3. Approve/reject/negotiate 4. Update TD e-288 if funding changes 5. Distribute approved document | Simple changes: 3-7 days Complex: 7-14 days Must be approved before work proceeds |
| --- | --- | --- | --- | --- |

| E4 | PSAP inquires about invoice status, payment delay, or requests invoice copy | Process 5 (Invoice Verification) | 1. Check invoice in system or mailbox 2. Verify against TD e-288 & SOW 3. Identify issue or confirm status 4. Respond to PSAP with explanation or ETA 5. Escalate to Finance if needed | Response: 1-3 business days Resolution of issues: 3-10 days depending on cause |
| --- | --- | --- | --- | --- |

| E5 | Vendor requests written confirmation that TD e-288 / funding has been issued before starting procurement or installation | Process 3 (TD e-288 Management) | 1. Verify TD e-288 status 2. Confirm allotment amount & any conditions 3. Provide formal confirmation letter/email 4. Copy PSAP advisor | Same day to 2 business days (high priority for scheduling) |
| --- | --- | --- | --- | --- |

| E6 | Other Cal OES branch/division (Finance, NG9-1-1 Planning, etc.) requests aggregate project status, funding utilization, or county-level report | Process 6 (Status Reporting) | 1. Pull data from internal trackers 2. Compile summary report or dashboard extract 3. Review for accuracy 4. Deliver to requesting party 5. Offer context or follow-up meeting if needed | Standard requests: 2-5 business days Complex/custom reports: 5-10 days |
| --- | --- | --- | --- | --- |

## 2.2 Top Internal Requests (Supervisors, Team-mates, Close Cal OES Personnel)

| # | Request Description & Source | Triggers Process | Sequential Steps & Actions | Typical Timeline |
| --- | --- | --- | --- | --- |

| I1 | Supervisor requests updated status report, risk assessment, or project pipeline summary for assigned counties | Process 6 (Status Reporting) | 1. Update all county trackers 2. Identify risks/delays 3. Prepare summary report or dashboard 4. Review with supervisor 5. Discuss any needed escalations or resource needs | Weekly standing: 1 day prep Ad-hoc: Same or next day |
| --- | --- | --- | --- | --- |

| I2 | Central Invoicing / Finance team requests verification that invoice amount does not exceed approved TD e-288 total before processing payment | Process 5 (Invoice Verification) | 1. Pull TD e-288 record 2. Compare invoice total vs remaining approved balance 3. Confirm or flag overage 4. Provide written verification or explanation 5. Update financial tracker | Response: Same day to 2 business days (payment critical) |
| --- | --- | --- | --- | --- |

| I3 | Team-mate or another advisor requests history, contact info, or lessons learned from a specific PSAP project | Process 6 or 10 (as needed) | 1. Search project files / tracker 2. Summarize relevant history or contacts 3. Share key documents or notes 4. Offer context or introduction if helpful | Simple lookup: Same day Complex history: 1-2 days |
| --- | --- | --- | --- | --- |

# 3. Top 10 Most Commonly Used Forms & Documents

These documents are central to nearly every process and request listed above. They are either required by the RFP/Attachments or have become standard operational tools post-award.

| # | Form / Document Name | Primary Purpose & When Used | Related Processes / Requests |
| --- | --- | --- | --- |

| 1 | Advance Notification for CPE Funding (Attachment 11) | PSAP formally requests funding allotment for CPE replacement (Cloud or On-Prem). Includes PSAP details, fiscal year, and solution type selection. | Triggers Process 1. Used in E1. Starts the entire project funding lifecycle. Submitted to assigned county advisor. |
| --- | --- | --- | --- |

| 2 | TD e-288 (Funding Authorization / Tracking Document) | Official state tracking and authorization of approved funding amount for a specific PSAP CPE project. Acts as the “purchase order” equivalent. | Core of Processes 1, 3, 4, 5. Referenced on every invoice (mandatory per Att. 14). Updated for change orders. E5 confirmation requests. |
| --- | --- | --- | --- |

| 3 | Statement of Work (SOW) – Based on Attachment 16 Sample SOW Template | Detailed project scope document between Vendor and PSAP. Covers overview, design, schedule, responsibilities, maintenance, training, acceptance, and appendices. | Central to Process 2. E2 submissions. Sections drive Processes 4, 7, 8, 9. Required before installation. Includes pricing from Exhibit C workbooks. |
| --- | --- | --- | --- |

| 4 | System Acceptance Checklist (TD284) | Standardized checklist used to verify all CPE functions work correctly before formal acceptance. Includes call flow, integrations, failover, recording, etc. | Core of Process 7. Required for final payments and start of monthly maintenance billing. Referenced in SOW section d and invoice instructions. |
| --- | --- | --- | --- |

| 5 | CPE Service Invoice Template (Attachment 15) + Instructions (Attachment 14) | Standardized invoice format with specific fields (TD e-288 ref, one-time vs monthly charges, acceptance date, service period, etc.). Must be used for all payments. | Drives Process 5. E4 status inquiries. Mandatory reference to TD e-288. One-time charges (Equipment/Labor) vs recurring maintenance clearly separated. |
| --- | --- | --- | --- |

| 6 | Change Order / Change Request Form (Vendor template + Branch approval record) | Formal document to request modifications to scope, price, or timeline after SOW approval. Requires PSAP + CA 9-1-1 Branch concurrence. | Triggers & core of Process 4. E3 submissions. Updates TD e-288 and SOW. Documented in project file for audit trail. |
| --- | --- | --- | --- |

| 7 | Site Certification Document & Floor Plan (SOW Appendices a & b) | Documents PSAP building/environmental requirements and physical layout for workstation deployment and network ingress point (especially important for On-Prem or hybrid). | Part of SOW (Process 2). Critical for On-Prem installations and site readiness milestone in schedule. Reviewed during design phase. |
| --- | --- | --- | --- |

| 8 | Training Attendance / Sign-off Form & Materials Delivery Record | Documents that required operator/supervisor training was delivered and attended. Includes quick reference guides and manual delivery confirmation. | Part of Process 9. Required per SOW section k. Collected at or immediately after training sessions. Filed in project closeout (Process 10). |
| --- | --- | --- | --- |

| 9 | Internal Project Status Tracker / Dashboard (County-level) | Advisor-maintained tracker or shared dashboard showing status of all active CPE projects per county (milestones, risks, financials, contacts). | Supports Process 6. Used for I1 supervisor requests and E6 cross-branch reports. Updated continuously from all other processes. |
| --- | --- | --- | --- |

| 10 | Post-Award Confidentiality Statement (Attachment 10) | Required signed statement from all personnel, agents, and subcontractors assigned to the awarded contract. Covers sensitive project and procurement information. | Collected at onboarding of new personnel or subcontractors. Maintained in project/compliance files. Referenced in closeout (Process 10) and any audit prep. |
| --- | --- | --- | --- |

## Summary Notes for Funding Advisors

- The Advance Notification (E1) is the single most important trigger — it starts the funding clock and gives PSAPs protected time to evaluate awarded vendors.

- TD e-288 is the central financial control document. Almost every financial action (invoices, change orders, closeout) references it.

- The SOW (based on Attachment 16) is the operational blueprint. Strong review upfront (Process 2) prevents most downstream issues with change orders and invoicing.

- Change Orders (Process 4) and Invoices (Process 5) are the highest-volume ongoing activities once projects are underway.

- Cloud vs On-Prem selection on the Advance Notification form significantly affects the SOW content (bandwidth vs physical site work) and should be confirmed early.

- Documentation discipline (especially archiving at closeout) is critical for audits and knowledge transfer between advisors.

This framework is derived directly from the requirements and forms in RFP 26-16743 and its attachments. It can be used for training new advisors, creating desk manuals, or building internal workflow tools / dashboards.